## Summary
QA Bug Report — Saucedemo.com
Project | Saucedemo.com — QA Testing
Site URL | https://www.saucedemo.com
Date Tested | April 2026
Tester | Alexander Villegas
Testing Type | Manual — Functional, UI/Visual, Content
Users Tested | standard_user, locked_out_user, problem_user
Bug Summary by Severity
Critical | 1
High | 4
Medium | 4
Low | 1
Total Bugs Found | 10

## Bug Reports
Bug ID | Title | Location | Pre-Condition | Steps To Reproduce | Expected Result | Actual Result | Severity | Status | Notes
BUG-001 | Raw code string displaying in product description | Inventory Page – Sauce Labs Backpack | Logged in as 'standard_user' | 1. Open https://www.saucedemo.com 2. Log in to saucedemo.com 3. Navigate to inventory page 4. Read Sauce Labs Backpack description 5. Observe bug in first description line | Clean, readable product description in plain English | Code string 'carry.allTheThings()' appears inline within the description text | Medium | Open
BUG-002 | Raw code string displaying in product title | Inventory Page - Test.allTheThings() T-Shirt (Red) | Logged in as 'standard_user' | 1. Open https://www.saucedemo.com 2. Log in to saucedemo.com 3. Navigate to inventory page 4. Read 'Test.allTheThings() T-Shirt (Red)' 5. Observe Title is Incorrect | Title to Read Sauce Labs T-shirt | Title Reads 'Test.allTheThings() T-Shirt (Red)' | Medium | Open
BUG-003 | Product image does not match product type | Inventory Page - Test.allTheThings() T-Shirt (Red) | Logged in as 'standard_user' | 1. Open https://www.saucedemo.com 2. Log in to saucedemo.com 3. Navigate to inventory page 4. Navigate to 'Test.allTheThings() T-Shirt (Red)' 5. Observe Product Image Does Not Match Title or Description | Image to be Sauce Labs Red T-shirt | Image displays a red/orange crewneck sweatshirt, not a T-shirt | Medium | Open
BUG-004 | Unprofessional language in locked out error message | Login Page | Logged in as locked_out_user | 1. Open https://www.saucedemo.com 2. Enter username: locked_out_user 3. Enter password: secret_sauce 4. Click Login 5. Observe error message | Clear and professional error message example: "This account has been locked. Please contact support." | Error message reads "Epic sadface: Sorry, this user has been locked out." | Low | Needs Clarification | Content/UI bug — flagged for product owner confirmation. May be intentional and fit brand and or enviornment. Would require clarification before logging as confirmed defect in production context.
BUG-005 | All product images replaced with incorrect identical image | Inventory Page | Logged in as problem_user | 1. Open https://www.saucedemo.com 2. Log in to saucedemo.com 3. Navigate to inventory page 4. Observe incorrect images on inventory page | All images are to be clear and correctly coordinate their respective product | All product images display an identical image of a dog holding a ball, unrelated to any listed product | High | Open | Affects all 6 products on inventory page
BUG-006 | Sort/filter dropdown is non-functional | Inventory Page | Logged in as problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user 3. Navigate to inventory page 4. Click the sort dropdown 5. Select any sort option, e.g., Price (low to high) 6. Observe product order | Products are reordered according to the selected sort option | Dropdown options appear, but selecting any option produces no change in product order | High | Open | Functional bug — core navigation feature is completely non-functional for this user. Sorting functional on standard_user — issue isolated to problem_user
BUG-007 | Add to Cart button unresponsive on specific products | Inventory Page | Logged in as problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user 3. Navigate to inventory page 4. Attempt to click Add to Cart on Sauce Labs Bolt T-Shirt, Sauce Labs Fleece Jacket, or Test.allTheThings() T-Shirt (Red) 6. Observe button response | Item is added to cart and button changes to Remove | Button is unresponsive — no item added, no state change | High | Open | Affects 3 specific products: Sauce Labs Bolt T-Shirt, Sauce Labs Fleece Jacket, Test.allTheThings() T-Shirt (Red). Persists after logout and back in. Remaining products can be added to cart
BUG-008 | Remove button non-functional on inventory page for three affected products | Inventory Page | Logged in as problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user 3. Navigate to inventory page 4. Add Sauce Labs Backpack, Sauce Labs Bike Light, or Sauce Labs Onsie to cart 5. Attempt to click Remove on inventory page 6. Observe button response | Remove button successfully removes item from cart and reverts to Add to Cart | Remove button is unresponsive — items cannot be removed from inventory page | High | Open | Workaround exists via cart page — but inventory page Remove button completely non-functional
BUG-009 | Autofill is non-functional on checkout form | Checkout Page | Logged in as problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user 3. Add item to cart 4. Navigate to cart and click Checkout 5. Attempt to use browser autofill on First Name, Last Name, or Zip fields 6. Observe the result | Browser autofill populates form fields correctly | Autofill does not function on any checkout form field | Medium | Open | Functional UX bug issue isolated to problem_user
BUG-010 | Last name input overwrites first name field on checkout form | Checkout Page | Logged in as problem_user | 1. Open https://www.saucedemo.com 2. Log in as problem_user 3. Add item to cart 4. Navigate to cart and click Checkout 5. Type first name into First Name field 6. Click Last Name field and begin typing 7. Observe disruption | Last name populates in Last Name field independently | Typing in Last Name field overwrites the First Name field content | Critical | Open | Critical UX/functional bug - blocks checkout completion entirely for problem_user. Directly impacts revenue flow.